DIGILYZR eWay

Home Screen — Build Plan, Components & Tooling

| Prepared by | Circle (for Affan) |
| --- | --- |
| For | DIGILYZR — eWay product & client review |
| Scope | Phase 1: Home dashboard, built to final quality |
| Target stack | Flutter (iOS first, Android to follow) |
| Companion doc | eWay v1 Scope & Flutter Mapping (strategy + full token mapping) |
| Date | 22 June 2026 |

Contents

# 1. Purpose of this document

This is the build plan for the eWay Home screen — the one screen we are taking to final quality first. It lists every component the Home screen is made of, the software tools and licences needed to build it (and what, if anything, we need to buy), and a phased task breakdown with effort estimates. The strategy and the full Flutter token mapping live in the companion scope document; this one is the practical “what we build and what it costs” sheet for the call.

Why Home only: It carries most daily usage and almost every problem in the current app, and it defines the design system (cards, charts, colours, type) that Modules and Reports are later assembled from. Perfect this one screen, ratify the system, and the rest is assembly rather than new design.

# 2. Home screen — component inventory

The Home screen breaks into the reusable components below. Each is a small Flutter widget that reads colours from the theme, so it works across all three colour schemes (Company Blue light, Company Blue dark, Emerald) with no rework. These same components later build Modules and Reports — which is why getting them right here matters.

| Component | What it does on Home | Flutter widget |
| --- | --- | --- |
| App header | Greeting, company/ACC context, profile avatar, sync control | EwayAppBar |
| Period filter | This month / Day / YTD / vs LY pills | FilterChipRow |
| Hero achievement card | The one lead number — achievement %, with sales vs target and a donut | HeroAchievementCard |
| Metric card | Day-to-date, coverage, calls — value + delta + mini bars/ring | MetricCard |
| Trend chart | 6-month / 4-quarter sales bars, tappable | TrendChartCard |
| Sales-mix card | Donut / ranked bars / share — the new alternative to the pie | SalesMixCard |
| Data table | Top brands — sortable, inline mini-bars, status pills | DataTableCard |
| Status pill | Good / watch / behind badge (colour-with-a-job) | StatusPill |
| Sync banner | Honest, human-readable sync state (replaces “Failed APIs”) | SyncBanner |
| Bottom tab bar | Home / Modules / + / Team / Reports, hide-on-scroll | EwayTabBar |

Reuse payoff: 10 components on Home cover an estimated 80%+ of what Modules, Team and Reports need. That is the dependency we are exploiting — Phase 1 builds the library, later phases assemble it.

# 3. Software tools & licences

The headline for the call: the core build needs nothing purchased. Flutter, the charting and all runtime libraries are free and open-source. The only spend is optional — a design handoff seat and the eventual app-store accounts, listed in section 3.2.

## 3.1 Build tools — free / open-source

| Tool | Use | Cost | Notes |
| --- | --- | --- | --- |
| Flutter SDK | App framework | Free | Open-source; iOS + Android from one codebase |
| fl_chart | Donut, bars, trend, sparklines | Free | Replaces the gauge images cleanly |
| riverpod | State + live theme switch | Free | Drives the 3-theme demo |
| drift / hive | Offline cache | Free | App opens with last-known data |
| local_auth | Face ID / fingerprint | Free | Login biometric unlock |
| connectivity_plus | Online/offline detection | Free | Powers the honest sync banner |
| google_fonts | Type scale | Free | Inter / SF-style across both platforms |
| VS Code / Android Studio | IDE | Free | Standard Flutter tooling |

## 3.2 Optional / situational spend

None of these block the Home build. They become relevant for design polish and, later, for shipping to the stores.

| Item | Use | Indicative cost | When needed |
| --- | --- | --- | --- |
| Figma (paid seat) | Editable design handoff & client mark-up | ~US$12–15 / editor / mo | Only if client wants editable Figma files; the interactive HTML already covers review |
| Apple Developer Program | TestFlight + App Store publishing | US$99 / year | At iOS release, not for the mock |
| Google Play Console | Play Store publishing | US$25 one-time | At Android release (later phase) |
| Icon / illustration pack | Polished module & empty-state art | US$0–80 one-time | Optional; current flat icon set is custom & free |
| Hosting for shareable demo | Public URL of the prototype | Free | Netlify / Vercel free tier is sufficient |

Bottom line for the call: Phase 1 (Home) needs US$0 in software. The only near-term decision is whether the client wants an editable Figma seat (~$12–15/mo). Store accounts ($99/yr Apple, $25 Google) come at release, not now.

# 4. Home screen — phased build plan

A practical sequence for delivering the Home screen to final quality. Estimates are working-day ranges for one developer and are indicative, to frame the conversation rather than commit a date.

| Step | Task | What gets done | Est. |
| --- | --- | --- | --- |
| 1 | Project & theme foundation | Flutter project, 3 ColorSchemes from the agreed tokens, theme provider, fonts | 1–2 d |
| 2 | Core components | Hero card, MetricCard, StatusPill, FilterChipRow, TappableListRow | 2–3 d |
| 3 | Charts | fl_chart donut, trend bars, sales-mix (donut/bars/share) with toggles | 2–3 d |
| 4 | Data table | Sortable Top-Brands table with inline bars + pills | 1–2 d |
| 5 | Sync banner & states | Honest sync/offline/empty states; remove raw error text | 1 d |
| 6 | Tab bar & assembly | Hide-on-scroll tab bar; compose full Home; wire mock data | 1–2 d |
| 7 | Polish & device test | Spacing, motion, light/dark, on-device iOS check | 1–2 d |

Indicative total: ~9–15 working days for a final-quality, themeable Home screen and the reusable component library beneath it.

Decision gate: After Home is signed off (the design system is ratified on it), Modules and Reports are assembly from these same components — not new design. That is where the time saving lands.

# 5. Summary for the 8 pm call

- Scope: build the Home dashboard to final quality first; it defines the system the rest reuses.

- Components: 10 reusable widgets cover Home and most of Modules/Reports later.

- Tools to buy: none for Phase 1. Core stack is free/open-source.

- Optional spend: Figma editor seat (~$12–15/mo) only if the client wants editable files; store accounts ($99/yr Apple, $25 Google) at release.

- Effort: ~9–15 working days for Home + the component library.

- Next gate: client sign-off on the Home design system before scaling to other screens.